## ProjectMonitoring
Programme | Batch | 2021 - 2025 | Project: | Analyzing Social Media Posts for Mental Health Disorder Detection
| Group | 29 | Names: | Soumyadeep Nandy, Prithwish Sarkar, Sagnik Mukhopadhyay, Arkapratim Ghosh
Attendance (Insert below names)
Date | Project discussions |  |  |  | Semester | Deliverable | Issues | Guide's remark | Soumyadeep Nandy | Prithwish Sarkar | Sagnik Mukhopadhyay | Arkapratim Ghosh
2024-07-03 | Topic Discussion |  |  |  | 7 |  |  |  | Present | Present | Present | Present
2024-07-17 | Additions to Project Rough Diagram 1 |  |  |  | 7 |  | Classifying whether text is positve or negative | Using CNN | Present | Present | Present | Present
2024-07-29 | Finalizing Project Rough Diagram 2 |  |  |  | 7 |  | Data extraction from social media | Web Scraping and sample code | Present | Present | Present | Present
2024-08-24 | Synopsis Discussion |  |  |  | 7 |  |  |  | Present | Present | Present | Present
2024-09-09 | Dataset and it's content |  |  |  | 7 |  | Extensive Dataset Required (Reddit + Twitter) | Using Reddit API and Kaggle datasets | Present | Present | Present | Present
2024-09-28 | Mid-term Deliverables |  |  |  | 7 |  | What to include in the project report | Using Latex all sections should be filled and analysis results till date should be inserted | Present | Present | Present | Present
2024-10-25 | Project Presentation and Prototype |  |  |  | 7 |  | What changes need to be made in PPT and Final Deployment | Seperate data collection for each class, XGBoost, improve interface | Present | Present | Present | Present
2024-11-14 | Modified Prototype Presentation |  |  |  | 7 |  | Can audio mood be analyzed for videos with no speech or text | Define a set of parameters for mapping mental issue to mental wellbeing | Present | Present | Present | Present
2024-12-15 | Additions made to the existing project after previous meet |  |  |  | 7 |  |  | Provide a brief writeup of all the added features and what all can be added in the next semester | Present | Present | Present | Present
2025-01-13 | Review PRD |  |  |  | 7 |  | ML Model workflow diagram | Give diagrams for the workflow of the web application instead of code | Present | Present | Present | Present
2025-01-15 | Prototype demo and PRD review |  |  |  | 7 |  |  |  | Present | Present | Present | Present
Total | [8 empty] | 100% | 100% | 100% | 100%
Overall | [8 empty] | 100% | 100% | 100% | 100%
Guide's signature:
(When maintained on hard-copy)

## Questions
Area | Question | Raised By | Status (Open / Closed) | Response | Response By
Topic Discussion | What classification model should be used for text? | Team | Closed | Using various algorithms like Naive Bayes, Random forest for a comparative study | Project Mentor
Additions to Rough Diagram 1 | What features should we extract from text data? | Team | Closed | Plan to use sentiment, keywords, and emotions. TF-IDF will be Helpful | Project Mentor
Rough Diagram 2 Finalization | What tools will be used for web scraping? | Team | Closed | Using Reddit API and sample Web scraping code | Project Mentor
Synopsis Discussion | How detailed should the project synopsis be? | Team | Closed | Synopsis should include a short Project overview | Project Mentor
Mid-term Deliverables | What format should the report follow? | Team | Closed | Use LaTeX and include all Analysis and results | Project Mentor
Presentation and Prototype | What changes need to be made in PPT? | Team | Closed | Implement different input types, Improve interface | Project Mentor
Video Analysis | Can audio be mood be analyzed if there is no speech or text in the video ? | Project Mentor | Closed | Using Frequency Analysis for preliminary classification. Using librosa module and MFCC | Team
Mapping mental issue to Mental wellbeing | Are there specific parameters for mapping mental issue to Mental wellbeing ? | Project Mentor | Closed | Changing the prompt for using Gemini API by adding Ryff's Scale of Psychological Wellbeing | Team
Detect facial emotions | How to detect facial expressions ? | Team | Closed | Using Deepface module of Python | Team
Image Description | Can situation depicted by an image be described ? | Team | Closed | Using Transformers (vit-gpt2 model) | Team
Model Retraining | Is only a single dataset considered the mother dataset all throughout the application ? | Project Mentor | Closed | No, model retraining is allowed if the user selects the option to analyze and retrain the model using the input | Team
Video Posts | Are videos from social media posts used ? | Project Mentor | Closed | Yes, video from twitter is extracted. Video and audio from reddit posts are extracted and combined to display in the website | Team
Visualization | Does a user get plain text result ? | Project Mentor | Closed | Graphs for emotion analysis, individual posts, overall probablities for each class after mental issue classification added | Team
Model Usage | Does the website implements single or multiple model ? | Project Mentor | Closed | Multiple models are used to create ensemble model and implemented in the website | Team
Dataset Size and Scalability | What observations were made regarding varying dataset size while model creation ? | Project Mentor | Closed | Accuracy varies. To keep the accuracy within acceptable variations, explored distributed architecture through sequential steps to show how bigger datasets can be divided into subsets, create models for those subsets, create ensemble model for each subset and finally combine them to have one final ensemble model | Team